## Colossus055
Filename	Starting page	Page count	Completed?	Pages completed	Worker	Date assigned
CONTRACT_AND_APPROVALS.s	1	1	1	1	Ron Burkey
ASSEMBLY_AND_OPERATION_INFORMATION.s	2	25	1	25	Ron Burkey
TAGS_FOR_RELATIVE_SETLOC.s	27	10	1	10	Ron Burkey
ERASABLE_ASSIGNMENTS.s	37	94	1	94	Ron Burkey
INTERRUPT_LEAD_INS.s	131	2	1	2	Fabrizio Bernardini	05/06/09
T4RUPT_PROGRAM.s	133	37	1	37	Fabrizio Bernardini	05/06/09
DOWNLINK_LISTS.s	170	11	1	11	Fabrizio Bernardini	05/06/09
FRESH_START_AND_RESTART.s	181	30		0	Fabrizio Bernardini	05/11/09
RESTART_TABLES.s	211	11		0	Fabrizio Bernardini	05/11/09
SXTMARK.s	222	14		0	Fabrizio Bernardini	05/11/09
EXTENDED_VERBS.s	236	32		0	Fabrizio Bernardini	05/11/09
PINBALL_NOUN_TABLES.s	268	17		0	Fabrizio Bernardini	05/11/09
CSM_GEOMETRY.s	285	12	1	12	Ron Burkey
IMU_COMPENSATION_PACKAGE.s	297	10	1	10	Ron Burkey
PINBALL_GAME_BUTTONS_AND_LIGHTS.s	307	83	1	83	Ron Burkey
R60_62.s	390	9	1	9	Ron Burkey
ANGLFIND.s	399	13	1	13	Ron Burkey
GIMBAL_LOCK_AVOIDANCE.s	412	2	1	2	Onno Hommes	05/06/09
KALCMANU_STEERING.s	414	6	1	6	Onno Hommes	05/06/09
SYSTEM_TEST_STANDARD_LEAD_INS.s	420	3	1	3	Onno Hommes	05/06/09
IMU_CALIBRATION_AND_ALIGNMENT.s	423	33	1	33	Onno Hommes	05/06/09
GROUND_TRACKING_DETERMINATION_PROGRAM.s	456	4	1	4	Onno Hommes	05/06/09
P34-35_P74-75.s	460	45	1	45	Onno Hommes	05/07/09
R31.s	505	6	1	6	Onno Hommes	05/07/09
P76.s	511	3	1	3	Hartmuth Gutsche	05/09/09
R30.s	514	11	1	11	Hartmuth Gutsche	05/09/09
STABLE_ORBIT.s	525	8	1	8	Hartmuth Gutsche	05/09/09
P11.s	533	18	1	18	Hartmuth Gutsche	05/09/09
TPI_SEARCH.s	551	11	1	11	Ron Burkey
P20-P25.s	562	73	1	73	Ron Burkey
P30-P37.s	635	14	1	14	Ron Burkey
P32-P33_P72-P73.s	649	35	1	35	Ron Burkey
P40-P47.s	684	53	1	53	Ron Burkey
P51-P53.s	737	48	1	48	Ron Burkey
LUNAR_AND_SOLAR_EPHEMERIDES_SUBROUTINES.s	785	4	1	4	Ron Burkey
P61-P67.s	789	30	1	30	Ron Burkey
SERVICER207.s	819	18	1	18	Ron Burkey
ENTRY_LEXICON.s	837	7	1	7	Ron Burkey
REENTRY_CONTROL.s	844	39	1	39	Ron Burkey
CM_BODY_ATTITUDE.s	883	7	1	7	Ron Burkey
P37_P70.s	890	44	1	44	Jim Lawton	05/10/09
S-BAND_ANTENNA_FOR_CM.s	934	2	1	2	Jim Lawton	05/10/09
LUNAR_LANDMARK_SELECTION_FOR_CM.s	936	1	1	1	Jim Lawton	05/10/09
TVCINITIALIZE.s	937	8	1	8	Jim Lawton	05/10/09
TVCEXECUTIVE.s	945	6	1	6	Ron Burkey
TVCMASSPROP.s	951	5	1	5	Ron Burkey
TVCRESTARTS.s	956	5	1	5	Ron Burkey
TVCDAPS.s	961	18	1	18	Ron Burkey
TVCSTROKETEST.s	979	5	1	5	Ron Burkey
TVCROLLDAP.s	984	15	1	15	Ron Burkey
MYSUBS.s	999	3	1	3	Ron Burkey
RCS-CSM_DIGITAL_AUTOPILOT.s	1002	23	1	23	Ron Burkey
AUTOMATIC_MANEUVERS.s	1025	12	1	12	Ron Burkey
RCS-CSM_DAP_EXECUTIVE_PROGRAMS.s	1037	2	1	2	Ron Burkey
JET_SELECTION_LOGIC.s	1039	24	1	24	Ron Burkey
CM_ENTRY_DIGITAL_AUTOPILOT.s	1063	30	1	30	Ron Burkey
DOWN-TELEMETRY_PROGRAM.s	1093	10	1	10	Ron Burkey
INTER-BANK_COMMUNICATION.s	1103	4	1	4	Ron Burkey
INTERPRETER.s	1107	93	1	93	Ron Burkey
FIXED_FIXED_CONSTANT_POOL.s	1200	5	1	5	Ron Burkey
INTERPRETIVE_CONSTANTS.s	1205	2	1	2	Ron Burkey
SINGLE_PRECISION_SUBROUTINES.s	1207	1	1	1	Ron Burkey
EXECUTIVE.s	1208	13	1	13	Ron Burkey
WAITLIST.s	1221	15	1	15	Ron Burkey
LATITUDE_LONGITUDE_SUBROUTINES.s	1236	7	1	7	Ron Burkey
PLANETARY_INERTIAL_ORIENTATION.s	1243	9	1	9	Ron Burkey
MEASUREMENT_INCORPORATION.s	1252	10	1	10	Ron Burkey
CONIC_SUBROUTINES.s	1262	47	1	47	Ron Burkey
INTEGRATION_INITIALIZATION.s	1309	25	1	25	Ron Burkey
ORBITAL_INTEGRATION.s	1334	21	1	21	Ron Burkey
INFLIGHT_ALIGNMENT_ROUTINES.s	1355	10	1	10	Ron Burkey
POWERED_FLIGHT_SUBROUTINES.s	1365	8	1	8	Sergio Navarro	05/11/09
TIME_OF_FREE_FALL.s	1373	16	1	16	Sergio Navarro	05/11/09
STAR_TABLES.s	1389	5	1	5	Sergio Navarro	05/11/09
AGC_BLOCK_TWO_SELF-CHECK.s	1394	10	1	10	Sergio Navarro	05/11/09
PHASE_TABLE_MAINTENANCE.s	1404	10	1	10	Sergio Navarro	05/11/09
RESTARTS_ROUTINE.s	1414	6	1	6	Ron Burkey
IMU_MODE_SWITCHING_ROUTINES.s	1420	29	1	29	Sergio Navarro	05/10/09
KEYRUPT_UPRUPT.s	1449	3	1	3	Ron Burkey
DISPLAY_INTERFACE_ROUTINES.s	1452	33	1	33	Ron Burkey
SERVICE_ROUTINES.s	1485	8	1	8	Ron Burkey
ALARM_AND_ABORT.s	1493	4	1	4	Ron Burkey
UPDATE_PROGRAM.s	1497	11	1	11	Ron Burkey
RT8_OP_CODES.s	1508	9	1	9	Ron Burkey
Total	1517	1516	79	1412

## Luminary099
Filename	Starting page	Page count	Completed?	Pages completed	Worker	Date assigned
CONTRACT_AND_APPROVALS.s	1	1	1	1	Ron Burkey
ASSEMBLY_AND_OPERATION_INFORMATION.s	2	26	1	26	Jim Lawton	05/13/09
TAGS_FOR_RELATIVE_SETLOC.s	28	10	1	10	Jim Lawton	05/13/09
CONTROLLED_CONSTANTS.s	38	16	1	16	Jim Lawton	05/13/09
INPUT_OUTPUT_CHANNEL_BIT_DESCRIPTIONS.s	54	7	1	7	Onno Hommes	05/14/09
FLAGWORD_ASSIGNMENTS.s	61	29	1	29	Onno Hommes	05/14/09
ERASABLE_ASSIGNMENTS.s	90	63	1	63	Onno Hommes	05/14/09
INTERRUPT_LEAD_INS.s	153	2	1	2	Onno Hommes	05/14/09
T4RUPT_PROGRAM.s	155	35		0	Hartmuth Gutsche	05/14/09
RCS_FAILURE_MONITOR.s	190	3		0	Hartmuth Gutsche	05/14/09
DOWNLINK_LISTS.s	193	13		0	Hartmuth Gutsche	05/14/09
AGS_INITIALIZATION.s	206	5		0	Hartmuth Gutsche	05/14/09
FRESH_START_AND_RESTART.s	211	27		0	Hartmuth Gutsche	05/14/09
RESTART_TABLES.s	238	6		0	Sergio Navarro	05/16/09
AOTMARK.s	244	18		0	Sergio Navarro	05/16/09
EXTENDED_VERBS.s	262	39		0	Sergio Navarro	05/16/09
PINBALL_NOUN_TABLES.s	301	19		0	Sergio Navarro	05/16/09
LEM_GEOMETRY.s	320	6	1	6	Ron Burkey
IMU_COMPENSATION_PACKAGE.s	326	12	1	12	Ron Burkey
R63.s	338	4	1	4	Ron Burkey
ATTITUDE_MANEUVER_ROUTINE.s	342	22	1	22	Ron Burkey
GIMBAL_LOCK_AVOIDANCE.s	364	1	1	1	Ron Burkey
KALCMANU_STEERING.s	365	5	1	5	Ron Burkey
SYSTEM_TEST_STANDARD_LEAD_INS.s	370	3	1	3	Ron Burkey
IMU_PERFORMANCE_TEST_2.s	373	9	1	9	Ron Burkey
IMU_PERFORMANCE_TESTS_4.s	382	8	1	8	Ron Burkey
PINBALL_GAME_BUTTONS_AND_LIGHTS.s	390	82		0	Jim Lawton	05/16/09
R60_62.s	472	14	1	14	Ron Burkey
S-BAND_ANTENNA_FOR_LM.s	486	4	1	4	Ron Burkey
RADAR_LEADIN_ROUTINES.s	490	2	1	2	Ron Burkey
P20-P25.s	492	122		0	Onno Hommes	05/15/09
P30_P37.s	614	4	1	4	Ron Burkey
P32-P35_P72-P75.s	618	33		0
LAMBERT_AIMPOINT_GUIDANCE.s	651	3		0
GROUND_TRACKING_DETERMINATION_PROGRAM.s	654	4		0
P34-35_P74-75.s	658	45		0
R31.s	703	6		0
P76.s	709	3		0
R30.s	712	11		0
STABLE_ORBIT.s	723	8		0
BURN_BABY_BURN--MASTER_IGNITION_ROUTINE.s	731	21		0
P40-P47.s	752	33		0
THE_LUNAR_LANDING.s	785	8		0
THROTTLE_CONTROL_ROUTINES.s	793	5		0
LUNAR_LANDING_GUIDANCE_EQUATIONS.s	798	31		0
P70-P71.s	829	9		0
P12.s	838	5		0
ASCENT_GUIDANCE.s	843	14		0
SERVICER.s	857	41		0
LANDING_ANALOG_DISPLAYS.s	898	10		0
FINDCDUW--GUIDAP_INTERFACE.s	908	18		0
P51-P53.s	926	58		0
LUNAR_AND_SOLAR_EPHEMERIDES_SUBROUTINES.s	984	4		0
DOWN_TELEMETRY_PROGRAM.s	988	10		0
INTER-BANK_COMMUNICATION.s	998	4		0
INTERPRETER.s	1002	93		0
FIXED_FIXED_CONSTANT_POOL.s	1095	5		0
INTERPRETIVE_CONSTANT.s	1100	2		0
SINGLE_PRECISION_SUBROUTINES.s	1102	1		0
EXECUTIVE.s	1103	14		0
WAITLIST.s	1117	16		0
LATITUDE_LONGITUDE_SUBROUTINES.s	1133	7		0
PLANETARY_INERTIAL_ORIENTATION.s	1140	9		0
MEASUREMENT_INCORPORATION.s	1149	10		0
CONIC_SUBROUTINES.s	1159	46		0
INTEGRATION_INITIALIZATION.s	1205	22		0
ORBITAL_INTEGRATION.s	1227	22		0
INFLIGHT_ALIGNMENT_ROUTINES.s	1249	10		0
POWERED_FLIGHT_SUBROUTINES.s	1259	9		0
TIME_OF_FREE_FALL.s	1268	16		0
AGC_BLOCK_TWO_SELF_CHECK.s	1284	10		0
PHASE_TABLE_MAINTENANCE.s	1294	9		0
RESTARTS_ROUTINE.s	1303	6		0
IMU_MODE_SWITCHING_ROUTINES.s	1309	29		0
KEYRUPT_UPRUPT.s	1338	3		0
DISPLAY_INTERFACE_ROUTINES.s	1341	33		0
SERVICE_ROUTINES.s	1374	7		0
ALARM_AND_ABORT.s	1381	5		0
UPDATE_PROGRAM.s	1386	11		0
RTB_OP_CODES.s	1397	6		0
T6-RUPT_PROGRAMS.s	1403	3		0
DAP_INTERFACE_SUBROUTINES.s	1406	4		0
DAPIDLER_PROGRAM.s	1410	11		0
P-AXIS_RCS_AUTOPILOT.s	1421	21		0
Q_R-AXIS_RCS_AUTOPILOT.s	1442	18		0
TJET_LAW.s	1460	10		0
KALMAN_FILTER.s	1470	2		0
TRIM_GIMBAL_CNTROL_SYSTEM.s	1472	13		0
AOSTASK_AND_AOSJOB.s	1485	22		0
SPS_BACK-UP_RCS_CONTROL.s	1507	4		0
Totals	1511	1510	21	248

## Artemis072
Filename	Starting page	Page count	Completed?	Pages completed	Worker	Date assigned
$ASSEMBLY_AND_OPERATION_INFORMATION.agc	1	26	1	26	Jim Lawton	09/02/09
$TAGS_FOR_RELATIVE_SETLOC.agc	27	9	1	9	Onno Hommes	07/25/09
$ABSOLUTE_LOCATIONS_FOR_UPDATES.agc	36	1	1	1	Onno Hommes	07/25/09
$SUBROUTINE_CALLS.agc	37	1	1	1	Onno Hommes	07/25/09
$ERASABLE_ASSIGNMENTS.agc	38	97		0	Onno Hommes	07/25/09
$CHECK_EQUALS_LIST.agc	135	4	1	4	Jim Lawton	07/25/09
$INTERRUPT_LEAD_INS.agc	139	2	1	2	Jim Lawton	07/25/09
$T4RUPT_PROGRAM.agc	141	38	1	38	Jim Lawton	07/25/09
$DOWNLINK_LISTS.agc	179	13	1	13	Jim Lawton	07/25/09
$FRESH_START_AND_RESTART.agc	192	37	1	37	Jim Lawton	07/25/09
$RESTART_TABLES.agc	229	10	1	10	Jim Lawton	07/25/09
$SXTMARK.agc	239	10	1	10	Jim Lawton	08/03/09
$EXTENDED_VERBS.agc	249	31	1	31	Jim Lawton	08/03/09
$PINBALL_NOUN_TABLES.agc	280	17	1	17	Jim Lawton	08/03/09
$CSM_GEOMETRY.agc	297	11	1	11	Jim Lawton	08/03/09
$IMU_COMPENSATION_PACKAGE.agc	308	10	1	10	Jim Lawton	08/03/09
$PINBALL_GAME_BUTTONS_AND_LIGHTS.agc	318	76	1	76	Jim Lawton	08/03/09
$R60_62.agc	394	9	1	9	Sergio Navarro	08/07/09
$ANGLFIND.agc	403	13	1	13	Sergio Navarro	08/07/09
$GIMBAL_LOCK_AVOIDANCE.agc	416	2	1	2	Sergio Navarro	08/07/09
$KALCMANU_STEERING.agc	418	6	1	6	Sergio Navarro	08/07/09
$SYSTEM_TEST_STANDARD_LEAD_INS.agc	424	3	1	3	Sergio Navarro	08/07/09
$IMU_CALIBRATION_AND_ALIGNMENT.agc	427	28	1	28	Sergio Navarro	08/07/09
$GROUND_TRACKING_DETERMINATION_PROGRAM.agc	455	8	1	8	Sergio Navarro	08/07/09
$P34-35_P74-75.agc	463	44	1	44	Sergio Navarro	08/07/09
$R31.agc	507	6		0	Hartmuth Gutsche	08/07/09
$P76.agc	513	3		0	Hartmuth Gutsche	08/07/09
$R30.agc	516	11		0	Hartmuth Gutsche	08/07/09
$P15.agc	527	7		0	Hartmuth Gutsche	08/07/09
$P11.agc	534	18		0	Hartmuth Gutsche	08/07/09
$P20-P25.agc	552	91		0	Hartmuth Gutsche	08/07/09
$P30-P31.agc	643	15	1	15	Jim Lawton	08/10/09
$P32-P33_P72-P73	658	33	1	33	Jim Lawton	08/10/09
$P40-P47.agc	691	51	1	51	Jim Lawton	08/10/09
$P51-P53.agc	742	47	1	47	Jim Lawton	08/10/09
$LUNAR_AND_SOLAR_EPHEMERIDES_SUBROUTINES.agc	789	3	1	3	Jim Lawton	08/10/09
$P61-P67.agc	792	31	1	31	Jim Lawton	08/10/09
$SERVICER207.agc	823	19	1	19	Jim Lawton	08/10/09
$ENTRY_LEXICON.agc	842	10	1	10	Jim Lawton	08/10/09
$REENTRY_CONTROL.agc	852	38	1	38	Jim Lawton	08/10/09
$CM_BODY_ATTITUDE.agc	890	7	1	7	Steve Case	08/17/09
$P37_P70.agc	897	43	1	43	Steve Case	08/17/09
$S-BAND_ANTENNA_FOR_CM.agc	940	3	1	3	Steve Case	08/17/09
$TVCINITIALIZE.agc	943	7	1	7	Steve Case	08/17/09
$TVCEXECUTIVE.agc	950	4	1	4	Steve Case	08/17/09
$TVCMASSPROP.agc	954	5	1	5	Steve Case	08/17/09
$TVCRESTARTS.agc	959	5	1	5	Steve Case	08/17/09
$TVCDAPS.agc	964	18	1	18	Steve Case	08/17/09
$TVCROLLDAP.agc	982	15	1	15	Steve Case	08/17/09
$MYSUBS.agc	997	3	1	3	Sergio Navarro	08/19/09
$RCS-CSM_DIGITAL_AUTOPILOT.agc	1000	24	1	24	Sergio Navarro	08/19/09
$AUTOMATIC_MANEUVERS.agc	1024	12	1	12	Sergio Navarro	08/19/09
$RCS-CSM_DAP_EXECUTIVE_PROGRAMS.agc	1036	2	1	2	Sergio Navarro	08/19/09
$JET_SELECTION_LOGIC.agc	1038	25	1	25	Sergio Navarro	08/19/09
$CM_ENTRY_DIGITAL_AUTOPILOT.agc	1063	30	1	30	Sergio Navarro	08/19/09
$DOWN-TELEMETRY_PROGRAM.agc	1093	11	1	11	Sergio Navarro	08/19/09
$INTER-BANK_COMMUNICATION.agc	1104	4	1	4	Sergio Navarro	08/19/09
$INTERPRETER.agc	1108	92	1	92	Jim Lawton
$FIXED_FIXED_CONSTANT_POOL.agc	1200	5	1	5	Jim Lawton
$INTERPRETIVE_CONSTANTS.agc	1205	2	1	2	Jim Lawton
$SINGLE_PRECISION_SUBROUTINES.agc	1207	1	1	1	Jim Lawton
$EXECUTIVE.agc	1208	13	1	13	Jim Lawton
$WAITLIST.agc	1221	15	1	15	Jim Lawton
$LATITUDE_LONGITUDE_SUBROUTINES.agc	1236	7	1	7	Sergio Navarro	08/27/09
$PLANETARY_INERTIAL_ORIENTATION.agc	1243	9	1	9	Sergio Navarro	08/27/09
$MEASUREMENT_INCORPORATION.agc	1252	10	1	10	Sergio Navarro	08/27/09
$CONIC_SUBROUTINES.agc	1262	47	1	47	Sergio Navarro	08/27/09
$INTEGRATION_INITIALIZATION.agc	1309	24	1	24	Sergio Navarro	08/27/09
$ORBITAL_INTEGRATION.agc	1333	21	1	21	Jim Lawton
$INFLIGHT_ALIGNMENT_ROUTINES.agc	1354	10	1	10	Jim Lawton
$POWERED_FLIGHT_SUBROUTINES.agc	1364	7	1	7	Jim Lawton
$TIME_OF_FREE_FALL.agc	1371	16	1	16	Jim Lawton
$STAR_TABLES.agc	1387	5	1	5	Jim Lawton
$AGC_BLOCK_TWO_SELF-CHECK.agc	1392	10	1	10	Jim Lawton
$PHASE_TABLE_MAINTENANCE.agc	1402	9	1	9	Jim Lawton
$RESTARTS_ROUTINE.agc	1411	6	1	6	Jim Lawton
$IMU_MODE_SWITCHING_ROUTINES.agc	1417	28	1	28	Jim Lawton
$KEYRUPT_UPRUPT.agc	1445	3	1	3	Jim Lawton
$DISPLAY_INTERFACE_ROUTINES.agc	1448	30	1	30	Jim Lawton
$SERVICE_ROUTINES.agc	1478	8	1	8	Jim Lawton
$ALARM_AND_ABORT.agc	1486	4	1	4	Jim Lawton
$UPDATE_PROGRAM.agc	1490	11	1	11	Jim Lawton
$RT8_OP_CODES.agc	1501	6	1	6	Jim Lawton
Totals	1507	1506	76	1273

## Colossus237
Filename	Starting page	Page count	Completed?	Pages completed	Worker	Date assigned
$ASSEMBLY_AND_OPERATION_INFORMATION.agc	1	24		0	Sergio Navarro
$TAGS_FOR_RELATIVE_SETLOC.agc	25	9		0	Sergio Navarro
$ERASABLE_ASSIGNMENTS.agc	34	92		0	Sergio Navarro
$INTERRUPT_LEAD_INS.agc	126	2		0	Steve Case	09/13/09
$T4RUPT_PROGRAM.agc	128	37		0	Steve Case	09/13/09
$DOWNLINK_LISTS.agc	165	11		0	Steve Case	09/13/09
$FRESH_START_AND_RESTART.agc	176	28		0	Steve Case	09/13/09
$RESTART_TABLES.agc	204	11		0	Steve Case	09/13/09
$SXTMARK.agc	215	14		0	Steve Case	09/13/09
$EXTENDED_VERBS.agc	229	32		0
$PINBALL_NOUN_TABLES.agc	261	17		0
$CSM_GEOMETRY.agc	278	12		0
$IMU_COMPENSATION_PACKAGE.agc	290	10		0
$PINBALL_GAME_BUTTONS_AND_LIGHTS.agc	300	81		0
$R60_R62.agc	381	9		0
$ANGLFIND.agc	390	13		0
$GIMBAL_LOCK_AVOIDANCE.agc	403	2		0
$KALCMANU_STEERING.agc	405	6		0
$SYSTEM_TEST_STANDARD_LEAD_INS.agc	411	3		0
$IMU_CALIBRATION_AND_ALIGNMENT.agc	414	33		0
$GROUND_TRACKING_DETERMINATION_PROGRAM-P21.agc	447	3		0
$P34-35_P74-75.agc	450	44		0
$R31.agc	494	6		0
$P76.agc	500	3		0
$R30.agc	503	11		0
$STABLE_ORBIT_P38-P39.agc	514	8		0
$P11.agc	522	17		0
$TPI_SEARCH.agc	539	11		0
$P20-P25.agc	550	74		0
$P30-P37.agc	624	13		0
$P40-P47.agc	637	53		0
$P51-P53.agc	690	46		0
$LUNAR_AND_SOLAR_EPHEMERIDES_SUBROUTINES.agc	736	4		0
$P61-P67.agc	740	30		0
$SERVICER207.agc	770	18		0
$ENTRY_LEXICON.agc	788	7		0
$REENTRY_CONTROL.agc	795	38		0
$CM_BODY_ATTITUDE.agc	833	7		0
$P37_P70.agc	840	44		0
$S-BAND_ANTENNA_FOR_CM.agc	884	2		0
$LUNAR_LANDMARK_SELECTION_FOR_CM.agc	886	10		0
$TVCINITIALIZE.agc	896	4		0
$TVCEXECUTIVE.agc	900	8		0
$TVCMASSPROP.agc	908	5		0
$TVCRESTARTS.agc	913	5		0
$TVCDAPS.agc	918	22		0
$TVCSTROKETEST.agc	940	5		0
$TVCROLLDAP.agc	945	13		0
$TVCGEN3FILTERS.agc	958	9		0
$MYSUBS.agc	967	3		0
$RCS-CSM_DIGITAL_AUTOPILOT.agc	970	23		0
$AUTOMATIC_MANEUVERS.agc	993	12		0
$RCS-CSM_DAP_EXECUTIVE_PROGRAMS.agc	1005	2		0
$JET_SELECTION_LOGIC.agc	1007	24		0
$CM_ENTRY_DIGITAL_AUTOPILOT.agc	1031	29		0
$DOWN-TELEMETRY_PROGRAM.agc	1060	10		0
$INTER-BANK_COMMUNICATION.agc	1070	4		0
$INTERPRETER.agc	1074	93		0
$FIXED_FIXED_CONSTANT_POOL.agc	1167	5		0
$INTERPRETIVE_CONSTANTS.agc	1172	2		0
$SINGLE_PRECISION_SUBROUTINES.agc	1174	1		0
$EXECUTIVE.agc	1175	13		0
$WAITLIST.agc	1188	15		0
$LATITUDE_LONGITUDE_SUBROUTINES.agc	1203	7		0
$PLANETARY_INERTIAL_ORIENTATION.agc	1210	9		0
$MEASUREMENT_INCORPORATION.agc	1219	9		0
$CONIC_SUBROUTINES.agc	1228	47		0
$INTEGRATION_INITIALIZATION.agc	1275	23		0
$ORBITAL_INTEGRATION.agc	1298	21		0
$INFLIGHT_ALIGNMENT_ROUTINES.agc	1319	10		0
$POWERED_FLIGHT_SUBROUTINES.agc	1329	8		0
$TIME_OF_FREE_FALL.agc	1337	16		0
$STAR_TABLES.agc	1353	5		0
$AGC_BLOCK_TWO_SELF-CHECK.agc	1358	10		0
$PHASE_TABLE_MAINTENANCE.agc	1368	10		0
$RESTARTS_ROUTINE.agc	1378	6		0
$IMU_MODE_SWITCHING_ROUTINES.agc	1384	29		0
$KEYRUPT_UPRUPT.agc	1413	3		0
$DISPLAY_INTERFACE_ROUTINES.agc	1416	33		0
$SERVICE_ROUTINES.agc	1449	8		0
$ALARM_AND_ABORT.agc	1457	4		0
$UPDATE_PROGRAM.agc	1461	11		0
$RTB_OP_CODES.agc	1472	8		0
Total:	1480	1479	0	0

## Solarium055
Filename	Starting page	Page count	Completed?	Pages completed	Worker	Date assigned
$ASSEMBLY_AND_OPERATION_INFORMATION.agc	1	11		0
$ERASABLE_ASSIGNMENTS.agc	12	23		0
$INTERRUPT_TRANSFER_ROUTINES.agc	35	2		0
$FIXED-FIXED_INTERPRETER_SECTION.agc	37	33		0
$BANK_03_INTERPRETER_SECTION.agc	70	28		0
$EXECUTIVE.agc	98	13		0
$WAITLIST.agc	111	9		0
$RESTART_CONTROL.agc	120	5		0
$501_RESTART_TABLES_AND_ROUTINES.agc	125	15		0
$FRESH_START_AND_RESTART.agc	140	11		0
$DOWN-TELEMETRY_PROGRAM.agc	151	8		0
$T4RUPT_OUTPUT_CONTROL_PROGRAMS.agc	159	31		0
$MODE_SWITCHING_AND_MARK_ROUTINES.agc	190	24		0
$IMU_COMPENSATION_PACKAGE.agc	214	10		0
$IRIG_PULSE-TORQUING_ROUTINES.agc	224	11		0
$EXTENDED_VERBS_FOR_MODING.agc	235	30		0
$AGC_SELF_CHECK.agc	265	26		0
$INTER-BANK_COMMUNICATION.agc	291	2		0
$ALARM_AND_DISPLAY_PROCEDURES.agc	293	3		0
$ORBITAL_INTEGRATION_PROGRAM.agc	296	30		0
$ORBITAL_INTEGRATION_FOR_501.agc	326	6		0
$PRELAUNCH_ALIGNMENT_PROGRAM.agc	332	34		0
$INFLIGHT_ALIGNMENT_PROGRAM.agc	366	8		0
$RTB_OP_CODES.agc	374	18		0
$IMU_PERFORMANCE_TESTS_1.agc	392	34		0
$IMU_PERFORMANCE_TESTS_2.agc	426	35		0
$INFLIGHT_ALIGNMENT_SUBROUTINES.agc	461	16		0
$KEYRUPT_UPRUPT_FRESH_START.agc	477	4		0
$PINBALL_GAME_BUTTONS_AND_LIGHTS.agc	481	72		0
$501_MISSION_CONTROL_PROGRAM.agc	553	75		0
$POWERED_FLIGHT_SUBROUTINES.agc	628	54		0
$TIME_OF_FREE_FALL_CALCULATIONS.agc	682	15		0
$DUMMY_501_INITIALISATION.agc	697	1		0
$RE-ENTRY_CONTROL.agc	698	48		0
$AVERAGE_G_INTEGRATOR.agc	746	8		0
$VERIFICATION_ASSISTANCE_PROGRAMS.agc	754	5		0
$SUM-CHECK_END_OF_RECORD_MARKS.agc	759	3		0
Total:	762	761	0	0